## Sheet1
Main Task No. | Subtask No. | Application Module(s) | Application Service or Module | Main Task Description | Development Estimation of the Task (in man-days) | Unit Test Estimation (in man-days) | Total Dev for Main Task | Task Estimation Size | Priority | Additional Risk (in man-days) | Tentative Assignment | Sprint | Sprint man-days
1 | 1.1 | Application overall | Build the Skeleton of the application | Specify the structure of the source code | 0.25
1 | 1.2 | Application overall | Build the Skeleton of the application | Build the Skeleton of the application with all defined classes in the High Level Specs at the Abstract Level and on the Reusable or Native layers | 2
1 | 1.3 | Application overall | Build the Skeleton of the application | Create the GitHub Repository with application Skeleton | 0.25 |  | 2.5 | M | P1
2 | 2.1 | Configuration Services | Configuration Services overall | Write the details specification for ConfigurationServices | 1
2 | 2.2 | Configuration Services | Configuration Services overall | Implement the Abstract layer for Configuration Services | 0.25
2 | 2.3 | Configuration Services | Service Container | Implement the Service Container Class main methods | 2
2 | 2.4 | Configuration Services | Service Locator | Implement the Service Locator | 2
2 | 2.5 | Configuration Services | Service Factories | Implement the Service Factories for all the Services in the scope | 1
2 | 2.6 | Configuration Services | PlaybackEngineConfigurator | Load PlackbackEngine description from the configuration Files | 2
2 | 2.7 | Configuration Services | Service Container | Implement the final logic | 1
2 | 2.8 | Configuration Services | Application Overall | Conditional generation of .js files based on the configured solution (Tizen, WebOS, Nodejs, firmware version, and possible customized services) configuration file | 4 | 2
2 | 2.9 | Configuration Services | Configuration Services overall | Unit Tests for load services configuration for WebOS Playback Engine |  | 0.5
2 | 2.10 | Configuration Services | Configuration Services overall | Unit Tests for load services configuration for Tizen Playback Engine |  | 0.5
2 | 2.11 | Configuration Services | Configuration Services overall | Unit Tests for load services configurationfor WebOS Playback Engine |  | 0.5 | 16.75 | XL | P2 |  |  | Sprint_01 | 19.25
3 | 3.1 | Transversal Services - SDK Services | Details Specifications for SDK Services | Details specifications for SDK Encapsulation (SDK Services) Note on the Details Specs and on the Implementation: Need to create a .d.ts description file for each SDK package that is used, next need to select from each package the used functions , then need to align their signatures in order to be treated in an uniform way via an abstract SDK Layer | 3
3 | 3.2 | Transversal Services - SDK Services | "Web OS SDK" Service | Encapsulate WebOS SDK (to be detailed) (N_SDK_WebOS and A_SDK_JsTV) | 5
3 | 3.3 | Transversal Services - SDK Services | "Tizen SDK" Service | Encapsulate Tizen SDK (to be detailed) | 5
3 | 3.4 | Transversal Services - SDK Services | "NodeJs SDK" Service | Encapsulate Node.js SDK (to be detailed) | 5
3 | 3.5 | Transversal Services - SDK Services | WebBrowser SDK | Encapsulate WebBrowser SDK (to be detailed) | 4
3 | 3.6 | Transversal Services - SDK Services | "Web OS SDK" Service | Unit tests for WebOS SDK |  | 0.5
3 | 3.7 | Transversal Services - SDK Services | "Tizen SDK" Service | Unit Tests for Tizen SDK |  | 0.5
3 | 3.8 | Transversal Services - SDK Services | "NodeJs SDK" Service | Unit Tests for NodeJs SDK |  | 0.5
3 | 3.9 | Transversal Services - SDK Services | WebBrowser SDK | Unit Tests for WebBrowser SDK |  | 0.5 | 24 | XL | P3 |  |  | Sprint_02+1.5 days | 24
4 | 4.1 | Transversal Service - "Utils Service | "Utils" Service | Details specifications for "Utils" Encapsulation (SDK Services) (concretly: review the SOC code and identify the main utils functions and/or reusable parts of ütils"code to be extracted/reused/encapsulated and the related js libraries | 1
4 | 4.1 | Transversal Service - "Utils Service | "Utils" Service | Implement the Abstract layer for Utils Services | 0.5
4 | 4.2 | Transversal Service - "Utils Service | "Utils" Service | Implement (encapsulate) date/time functions | 0.5
4 | 4.3 | Transversal Service - "Utils Service | "Utils" Service | Implement (encapsulate) string functions | 0.5
4 | 4.4 | Transversal Service - "Utils Service | "Utils" Service | Implement (encapsulate) number conversions and formatting functions | 0.5
4 | 4.5 | Transversal Service - "Utils Service | "Utils" Service | Implement (encapsulate) file functions (in addition to the SDK encapsulated functions) (the estimation is only a time buffer) | 0.5
4 | 4.6 | Transversal Service - "Utils Service | "Utils" Service | Implement (encapsulate) web functions (download, upload, etc...) | 1
4 | 4.7 | Transversal Services - "Utils Service | "Utils" Service | Implement (encapsulate) Guid (unique id) functions | 0.5
4 | 4.8 | Transversal Services - "Utils Service | "Utils" Service | Unit tests on the Utils |  | 1 | 6 | XL | P4
5 | 5.1 | Transversal Services | "Log" Service | Details Specs on Log Service (including remote logging, and having levels of errors, verbosity) - try to reuse/reencapsulate/parameterized what was done in SOC | 0.5
5 | 5.2 | Transversal Services | "Log" Service | Implement the Abstract layer for Log Service (including remote logging) | 0.5
5 | 5.3 | Transversal Services | "Log" Service | Implement the Log Service without Remoting Logging (trying to reuse the existing code). Note: The calls to the Log Service will be implemented by each service separately | 1
5 | 5.4 | Transversal Services | "Log" Service | Implement the Log service remote Logging (trying to reuse the existing code) | 1.5
5 | 5.5 | Transversal Services | "Log" Service | Log unit Tests (including remote logging) |  | 0.5 | 4 | L | P5 |  |  | Sprint_03_FirstWeek | 10
6 | 6.1 | Transversal Services | "ServiceConfiguration" File | Details Specs on ServiceConfigurator Note: Not to be confound with PlaybackEngineConfigurator Currently opening hours .xml and application config file was identified as custom configurations in SOC. The additional configuration file (ex. that one for chron service, monitoring, statistics etc.) will be included in the estimation of that services | 0.5
6 | 6.2 | Transversal Services | "ServiceConfiguration" File | Implement the Abstract layer for Configuration Services | 0.5
6 | 6.2 | Transversal Services | "ServiceConfiguration" File | Implements "ServiceConfigurator" as a list of "FileSettings" components, where each component can load one settings file | 1
6 | 6.3 | Transversal Services | "ServiceConfiguration" File | "Opening Hours" file configurator | 1 | 0.5
6 | 6.4 | Transversal Services | "ServiceConfiguration" File | "General Settings" file configurator | 1 | 0.5 | 5 | L | P6 |  |  | Next Sprints will be defined later
7 | 7.1 | Rendering Services | Rendering Services Overall | Details specifications for Reusable Rendering Services (ImageRendering, Fill Rect, Video Renderer, Hlml Renderer, RenderingZone) - try to reuse/reincapsulate/ the existing SOC code | 1.5
7 | 7.2 | Rendering Services | Rendering Services Overall | Implement the Abstract Layers for Rendering Services | 0.5
7 | 7.3 | Rendering Services | Simulator | Implement a Simple Simulator to can test in loop the main functionalities - create zone/ startupprepare renderingf service / play rendering service / destroy rendering zone scenarios, with different renderer types | 2
7 | 7.4 | Rendering Services | Image Renderer | Implement Image renderer (img) | 1.5
7 | 7.5 | Rendering Services | Image Renderer | Implement Image renderer Stretch, Fit, Fill , Normal, Centre functionalities | 1 | 0.5
7 | 7.6 | Rendering Services | Fill Rect Renderer | Implement Fill Rect Renderer (div) | 0.75 | 0.25
7 | 7.7 | Rendering Services | Background Renderer | Implement Html5 Background Renderer (div) | 1.5 | 0.25
7 | 7.8 | Rendering Services | Video Renderer | Implement Hrml5 Video Renderer (video) | 2 | 1
7 | 7.9 | Rendering Services | Html Renderer | Implement Html5 Html Renderer for HTML pages and for HTML5 template (iframe) | 3 | 1
7 | 7.10 | Rendering Services | Flash renderer | Implement Html5 Flash Renderer (object) | 2 | 1
7 | 7.11 | Rendering Services | Rendering Zone | Implement Html5 Rendering Zone (div) (manually test z-order during unit tests) | 1 | 1 | 21.75 | XL | P7
8 | 8.1 | Rendering Services | Native WebOS Video Renderer | Details specifications for Native WebOS Rendering Services | 1
8 | 8.2 | Rendering Services | Native WebOS Video Renderer | Realize a POC with different variants/settings of a Player based on the WebOS API | 5
8 | 8.3 | Rendering Services | Native WebOS Video Renderer | Implement Native Web OS Video Renderer | 5
8 | 8.4 | Rendering Services | Native WebOS Video Renderer | Units Test for native Web OS Video Renderer |  | 2 | 13 | XL | P8
9 | 9.1 | Rendering Services | Native Tizen Video Renderer | Details specifications for Native Tizen Rendering Services | 1
9 | 9.2 | Rendering Services | Native Tizen Video Renderer | Implement Native Tizen Video Renderer (by trying to recuperate and to re-encapsulate the existing code) | 2
9 | 9.2 | Rendering Services | Native Tizen Video Renderer | Units Test for native Tizen Video Renderer |  | 2 | 5 | L | P9
10 | 10.1 | Rendering Services | Screen Saver Renderer Service | Details Specification on Screen Saver Rendering Service (an abstract Renderer that can have embed inside different types of Rendering Services based on a configuration file) | 0.5
10 | 10.2 | Rendering Services | Screen Saver Renderer Service | Implement the Abstract layer for Screen Saver Service | 0.5
10 | 10.3 | Rendering Services | Screen Saver Renderer Service | Read the screen saver configuration file (by a distinct FileConfigurator Class part of ServiceConfigurator) | 1.5
10 | 10.4 | Rendering Services | Screen Saver Renderer Service | Implement the Screen Saver (try to reuse / re-encapsulate) the SOC code but using the new Renderer Service Class) | 1.5
10 | 10.5 | Rendering Services | Screen Saver Renderer Service | Unit Tests on Screen Saver Class using different renderers |  | 1 | 5 | L | P10
11 | 11.1 | Non-Rendering Service | Chron Service | Details Specs on Chron Service (we will leverage the windows service implementation from a functional point of view) Note: The implementation of the Chron Service at this stage (=before the implementation of the Core Services) is neeeded beacuse the Playlist Watcher will be started periodically by the Chron Service. The term "Service" is not used here as ¨OS Service" | 0.5
11 | 11.2 | Non-Rendering Services | Chron Service | Implement the Abstract layer for Chron Services | 0.5
11 | 11.3 | Non-Rendering Services | Chron Service | Implement the loading of Chron Services configuration file (as a distinct File Configurator inside the ServiceConfigurator | 1.5
11 | 11.4 | Non-Rendering Services | Chron Service | Implement the Chron Service | 1.5
11 | 11.5 | Non-Rendering Services | Chron Service | Unit Tests on Chron Service |  | 0.5 | 4.5 | L | P11
12 | 12.1 | Core Services | Playlist watcher | Details Specs of Playlist Watcher Note: This service monitor if a new playlist is available for download | 0.5
12 | 12.2 | Core Services | Playlist watcher | Implement the Abstract layer for Playlist Watcher | 0.25
12 | 12.3 | Core Services | Playlist watcher | Implement the Playlist Watcher Service | 2
12 | 12.4 | Core Services | Playlist watcher | Unit Tests for Playlist Watcher |  | 0.5 | 3.25 | L | P12
13 | 13.1 | Core Services | Playlist Downloader | Detailed Specs on Playlist downloader | 0.5
13 | 13.2 | Core Services | Playlist Downloader | Implement the Abstract layer for Playlist Downloader | 0.5
13 | 13.3 | Core Services | Playlist Downloader | Implementation of Playlist Downloader Service (try to leverage the existing SOC code) | 4
13 | 13.4 | Core Services | Playlist Downloader | Unit tests on service Downloader (need to tests the situations where the playlist cannot be downloaded or some media items cannot be downloaded or we have interruptions during download) |  | 3 | 8 | XL | P13
14 | 14.1 | Core Services | Playlist Controller (= echiv. of JOW) | Details Specs for Playlist Controller Service (1. trying to align with JOW for a functional perspective 2. need to well detailed this critical part including the unit tests cases) Blue Color = means "Critical" Component ) | 3
14 | 14.2 | Core Services | Playlist Controller (= echiv. of JOW) | Implement the Abstract layer for Playlist Downloader (trying to align the external interfaces close to Jow) | 1
14 | 14.3 | Core Services | Playlist Controller (= echiv. of JOW) | Implement the Playlist Controller (trying to leverage parts of SOC, need to decouple the playlist controller part for the rendering controller part) | 14
14 | 14.3 | Core Services | Playlist Controller (= echiv. of JOW) | Unit Tests for Playlist Controller (unit test on Durations, Playlist Loop, Tag Component, Design Component) |  | 5 | 23 | XL | P14
15 | 15.1 | Core Services | Rendering Controller | Detailed Specs for Service Controller (need to well detail this critical part including the unit tests cases) Blue Color = means "Critical" Component | 2
15 | 15.2 | Core Services | Rendering Controller | Implement the Abstract layer of Playllsit controller | 1
15 | 15.3 | Core Services | Rendering Controller | Implement RenderingZoneList subcomponent | 2
15 | 15.4 | Core Services | Rendering Controller | Implement RenderingServiceList subcomponent | 2
15 | 15.4 | Core Services | Rendering Controller | Implement the Rendering Controller logic | 4
15 | 15.5 | Core Services | Rendering Controller | Add to the Rendering Controller the logic to generate the information need by Statistics Service | 1.5
15 | 15.6 | Core Services | Rendering Controller | Unit Tests of Rendering Controller |  | 3 | 15.5 | XL | P15
16 | 16.1 | Non Rendering Services | LiveCommands Service | Detailed Specs of Live Commands Service (trying to leverage the existing SOC Code) | 0.5
16 | 16.2 | Non Rendering Services | LiveCommands Service | Implement the Abstract Layer of LiveCommand Service | 0.25
16 | 16.3 | Non Rendering Services | LiveCommands Service | Implements the Live Commands Service | 2
16 | 16.4 | Non Rendering Services | LiveCommands Service | Unit Test For Live Command Service |  | 0.5 | 3.25 | L | P24
17 | 17.1 | Non-Rendering Services | Monitoring Service | Detailed Specs on Monitoring Service (trying to leverage the SOC code) | 0.5
17 | 17.2 | Non-Rendering Services | Monitoring Service | Implement the Abstract Layer of Monitoring Service | 0.5
17 | 17.3 | Non-Rendering Services | Monitoring Service | Load the configuration file of Monitoring Service (by a distinct FileConfigurator Class part of ServiceConfigurator) | 1 | 0.25
17 | 17.4 | Non-Rendering Services | Monitoring Service | Implement the Screen Capture service | 2
17 | 17.5 | Non-Rendering Services | Monitoring Service | Implement the Monitoring Service | 2
17 | 17.6 | Non-Rendering Services | Monitoring Service | Unit Test on LogEngine Service |  | 1 | 7.25 | XL | P16
18 | 18.1 | Non-Rendering Services | LogEngine Service | Detailed Specs on LogEngine Service (The service that sent the log file to the server) Note: Not to be confound with the Log Service | 0.5
18 | 18.2 | Non-Rendering Services | LogEngine Service | Implement the Abstract Layer of LogEngine Service | 0.25
18 | 18.3 | Non-Rendering Services | LogEngine Service | Load the configuration files with the LogEngine parameters (by a distinct FileConfigurator Class part of ServiceConfigurator) | 1 | 0.25
18 | 18.4 | Non-Rendering Services | LogEngine Service | Implement the LogEngine Service | 1.5
18 | 18.5 | Non-Rendering Services | LogEngine Service | Unit Test on LogEngine Service |  | 1 | 4.5 | L | P17
19 | 19.1 | Non-Rendering Services | Statistics Service | Detailed Specs on Statitics Service (The service that sent the statistics with the media items that have completely played) | 0.5
19 | 19.2 | Non-Rendering Services | Statistics Service | Implement the Abstract Layer of Statistics Service | 0.25
19 | 19.3 | Non-Rendering Services | Statistics Service | Load the configuration files with the Statistics parameters (by a distinct FileConfigurator Class part of ServiceConfigurator) | 1 | 0.25
19 | 19.4 | Non-Rendering Services | Statistics Service | Implement the Statistics Service | 1.5
19 | 19.5 | Non-Rendering Services | Statistics Service | Unit Test on Statistics Service |  | 1 | 4.5 | L | P18
20 | 20.1 | Non-Rendering Services | PlayerFileUpdater Service | Detailed Specs on PlayerFileUpdater Service Note: is a service that verifies from time to time if a set of specified player files are in sync with the similar reference files hosted on the server. | 0.5
20 | 20.2 | Non-Rendering Services | PlayerFileUpdater Service | Implement the Abstract Layer of PlayerFileUpdater Service | 0.25
20 | 20.3 | Non-Rendering Services | PlayerFileUpdater Service | Load the configuration files of PlayerFileUpdater (by a distinct FileConfigurator Class part of ServiceConfigurator) | 1.25
20 | 20.4 | Non-Rendering Services | PlayerFileUpdater Service | Implement the PlayerFileUpdater Watcher Component (leverage the SOC Code) | 1
20 | 20.5 | Non-Rendering Services | PlayerFileUpdater Service | Implement the PlayerFileUpdater Download Component (leverage the SOC Code) | 2
20 | 20.6 | Non-Rendering Services | PlayerFileUpdater Service | Unit Test on PlayerFileUpdater Service |  | 0.5 | 5.5 | XL | P19
21 | 21.1 | Non-Rendering Services | EnvUpdater Service | Detailed Specs on EnvUpdater Note: This Service Does not exists on POC. To discuss if we will align or not with windows/android platforms, platforms that have this service The “Env.Updater” Service - is a service that on Windows/Android platforms verifies from time to time if a new Software / Hardware and/or Client Updates exist on the server and need to be downloaded by the client. If exist, they are downloaded and installed. | 1
21 | 21.2 | Non-Rendering Services | EnvUpdater Service | Implement the Abstract Layer of EnvUpdater Service | 0.5
21 | 21.3 | Non-Rendering Services | EnvUpdater Service | Implement the Watcher Component | 1.5
21 | 21.4 | Non-Rendering Services | EnvUpdater Service | Implement the Download Component | 3
21 | 21.5 | Non-Rendering Services | EnvUpdater Service | Implement the Installation of new Components (for the Software it can be a simple copy to the final folder) and the restart (but need to take care to well restart/recover in case of errors) | 2
21 | 21.6 | Non-Rendering Services | EnvUpdater Service | Unit Test Case |  | 1 | 9 | XL | P20
22 | 22.1 | Non-Rendering Services | The WatchDog Service | Detailed Specs on WatchDog Service Note: This Service Does not exists on POC | 0.5
22 | 22.2 | Non-Rendering Services | The WatchDog Service | Implement the Abstract Layer of WatchDog Service | 0.25
22 | 22.3 | Non-Rendering Services | The WatchDog Service | Load the configuration file that will contains the services that will be monitored by the WatchDog Service (by a distinct FileConfigurator Class part of ServiceConfigurator) | 1.5
22 | 22.4 | Non-Rendering Services | The WatchDog Service | Implement the WatchDog Service | 1.5
22 | 22.5 | Non-Rendering Services | The WatchDog Service | The monitored services needs to defined an to implement an interface to exposed their status | 1.5
22 | 22.6 | Non-Rendering Services | The WatchDog Service | Unit Test on WatchDog Service |  | 1 | 6.25 | XL | P21
23 | 23.1 | Non-Rendering Services | The Diagnostics Service | Detailed Specs of Diagnostic Service (trying to leverage the Android Diagnostics Service) | 1
23 | 23.2 | Non-Rendering Services | The Diagnostics Service | Implement the Abstract layer of Diagnostic Server | 0.5
23 | 23.3 | Non-Rendering Services | The Diagnostics Service | Implements the Diagnostics Service (considered about 4-5 html screens with different statistics and some commands) | 6
23 | 23.4 | Non-Rendering Services | The Diagnostics Service | Unit Test for Diagnostics Service |  | 1 | 8.5 | XL | P22
24 | 24.1 | Non Rendering Services | The Startup Service | Detailed Specs of Startup Service (identify all the setup to be done during the startup: ex: Tv volume level etc..) | 0.5
24 | 24.2 | Non Rendering Services | The Startup Service | Implement the Abstract Layer of Startup Service | 0.25
24 | 24.3 | Non Rendering Services | The Startup Service | Implement the Startup service | 1.75
24 | 24.4 | Non Rendering Services | The Startup Service | Unit test cases for Startup Service |  | 0.5 | 3 | M | P23
25 | 25.1 | Non Rendering Services | Purge Service | Detailed Spec For Purge Service and The Purge Conditions and Schedule | 0.5
25 | 25.2 | Non Rendering Services | Purge Service | Implement the Abstract Layer of Purge Service | 0.25
25 | 25.3 | Non Rendering Services | Purge Service | Implements the Purge Service | 1
25 | 25.4 | Non Rendering Services | Purge Service | Unit Test For Purge Service |  | 0.25 | 2 | M | P25
[5 empty] | Possible Roadmap | Total Man-Days | 209 | man-days
[6 empty] | Duration with 2 "continuos" resources | 5.225 | months
[6 empty] | Est. Start Day | 22-April-2019
[6 empty] | Est. End Day | 29-Oct-2019
29-Oct-2019 is the estimated End Date by considering 1 month vacation/ bankholidays)
[6 empty] | Integration/ Final Tests Ended (~1 Month ) | 30-Nov-2019
Roadmap adding 15% Risk (risk assesment)
[6 empty] | With Risk ~15% | 240.35 | man-days
[6 empty] | Duration with 2 "continuos" resources by adding 15% risk | 6.0088 | months
[6 empty] | Est. End day with 15% | 2019-11-22
[6 empty] | Duration with 15% risk | ~6 months
[6 empty] | Integration/ Final Tests (~1 Month ) | 22-Dec-2019
[6 empty] | Major Check Point End Sep 2019 | in 5 months (including 1 month vacation) | At the end of critical parts
For Release 2 or Next Releases
26 | … | Rendering service | VOD Service
27 | … | Rendering service | Audio Service
28 | … | Rendering service | TV/HDMI Pass Through Service
29 | … | Rendering service | Sync Playback Service
30 | … | Rendering service | Interactivity Service